**2025/2030 One-and-Six General Work Plan Information**

**Completed Projects:**

1. **C-23 (161): District 1, Alpha Rd.** 0.4 miles completed.

Scope of work -Grading, and Placed surface gravel, Completed in July of 2024.

1. **C-23 (152): District 1, Egan Rd.** 3.5 miles completed.

Scope of work- Grading and Placed surface gravel, Completed in August of 2024.

1. **C-23 (151A & 151B): District 1, Table Rd East side of highway.** 2.5 miles completed.

Scope of work-Grading and Placed surface gravel, completed September of 2024.

1. **C-23 (160): District 1, Davenport Rd.** 1.0 miles completed August 2024.

Scope of work- Restored ditches, restored fore slope, Grading and Placed surface gravel,

1. **C-23 (145): District 2, Grantham Rd.,** 0.5 miles completed September 2024.

Scope of work- Restored ditches, restored fore slope, grading, and placed surface gravel. Place CMP.

1. **C-23 (148): District 3, Crow Butte Rd.** 0.6 miles completed October of 2024.

Scope of work- Restored ditches, restored fore slope, Grading and Placed surface gravel.

1. **C-23 (112): Squaw Creek Rd.** 2.0 miles completed October of 2024

Scope of work- Restored ditches, restored fore slope, Grading and Placed surface gravel.

**One Year Projects:**

**District 1:** total amount of miles to complete in 2025 will be 9.9 miles of road. Davenport Rd. will be the primary focus to start, then Hughbanks, then Beaver Valley, and then Stewart.

1. **C-23 (150): District 1, Hughbanks Rd.** – 4.0 miles, carried over from the 2022 One Year Plan
2. **C-23 (127A & 127B): District 1, Stewart Rd.** – 1.4 miles, existing work plan
3. **C-23 (124): District 1, Beaver Valley Rd.** – 3.5 miles, existing work plan
4. **C-23 (160): District 1, Davenport Rd. –** 1.0 miles, Existing work plan

**District 2:** total amount of miles to complete in 2025 will be 9.0 miles of road. This project is a continuation, as only 1 mile of this project was completed from the 2022 1-year plan, and it is the only project planned for district 2 due to the amount of work required to complete the project.

1. **C-23 (149): District 2, Table Center Rd.** 9.0 miles, carried over from the 2022/2023 One Year Plan

**District 3:** total amount of miles to complete in 2025 will be 7.5 miles of road. Squaw Creek Rd. will be the initial focus. Then we will determine which of the next projects we will work on due to the weather conditions at that time.

1. **C-23 (143): District 3,** **Squaw Creek Rd.** 2.0 miles, carried over from the 2023 One Year Plan
2. **C-23 (111): District 3,** **N. Whitney Lake Rd.** 5.0 miles, carried over from the 2023 One Year Plan
3. **C-23 (136): District 3, Bergfield Rd.** 0.5 miles, carried over the 2023 One Year Plan

**Six Year Projects:**

1. **C-23 (164) Beaver Valley Rd. –** 3.0 miles in District 1
2. **C-23 (144) Deadhorse Rd. –** 6.0 miles in District2
3. **C-23 (104) West Ash Creek Rd.** – 2.0 miles in District 3
4. **C-23 (119) Lembke Rd.** – 1.3 miles in District 2
5. **C-23 (117) Hartman Rd.** – 2.4 miles in District 3
6. **C-23 (131) Arner Rd.** – 2.0 miles in District 3
7. **C-23 (162) Lemmon Rd.** 3.7 miles in District 3
8. **C-23 (163) McHenry Rd.** 3.0 miles District 1
9. **C-23 (129) Table Center Rd.** (Paving Project) – 1.8 miles in District 2
10. **C-23 (130) Pinney Rd.** – 1.0 miles in District 3
11. **C-23 (154) Breakneck Rd.** – 1.0 miles in District 3
12. **C-23 (155) Breakneck Rd.** – 1.5 miles in District 3
13. **C-23 (141) Table Rd.** – 2.6 miles in District 2
14. **C-23 (142) Squaw Creek Rd.** – 2.8 miles in District 3
15. **C-23 (153) Cottonwood School Rd.** – 7.0 miles in District 2
16. **C-23 (159A) County Road #50** – 0.7 miles in District 2
17. **C-23 (159B) County Road #50** – CMP installation in District 2

All road projects included in the 2030 Six Year Road Plan are being carried over from the 2029 Six Year Road Plan except for the additions of **Lemmon Rd. in District 3**, and **McHenry Rd. and Beaver Vally Rd. in District 1**, which are new work plans.